## Sheet1
Phase | Week | CRISP-DM Steps | Resources | Risks | Status | Comments
Milestone 1--Team Information/Communication Plan | Week-1 | Team Formation & Project Plan | Jay & Prashant | NA | Complete
Milestone 2--Data Selection and Project Proposal | Week-2 | Determine Business Objectives and Assess the Situation | Jay & Prashant |  | Not Started
| Week-2 | Source datasets and metadata details | Jay & Prashant |  | Not Started
| Week-2 | Requirements, assumptions and constraints | Jay & Prashant |  | Not Started
| Week-2 | What are the desired outputs of the project | Jay & Prashant |  | Not Started
| Week-2 | Peer Review: Evaluate Peers' Contributions to Group Projects | Jay & Prashant |  | Not Started
| Week-3 | What Questions Are We Trying To Answer? | Jay & Prashant |  | Not Started
| Week-3 | Data understanding | Jay & Prashant |  | Not Started
| Week-3 | Data preparation | Jay & Prashant |  | Not Started
| Week-4 | Correlations | Jay & Prashant |  | Not Started
| Week-4 | Peer Review: Evaluate Peers' Contributions to Group Projects | Jay & Prashant |  | Not Started
Milestone 3--Preliminary Analysis | Week-5 | Exploratory Data Analysis | Jay & Prashant |  | Not Started
| Week-5 | Modeling | Jay & Prashant |  | Not Started
| Week-6 | Modelling technique | Jay & Prashant |  | Not Started
| Week-6 | Parameter settings | Jay & Prashant |  | Not Started
| Week-6 | Peer Review: Evaluate Peers' Contributions to Group Projects | Jay & Prashant |  | Not Started
| Week-7 | Build Model | Jay & Prashant |  | Not Started
| Week-7 | Evaluation | Jay & Prashant |  | Not Started
| Week-8 | Peer Review: Evaluate Peers' Contributions to Group Projects | Jay & Prashant |  | Not Started
Milestone 4--Project Presentation & Status | Week-9 | Deployment | Jay & Prashant |  | Not Started
| Week-10 | Creating final Code files | Jay & Prashant |  | Not Started
| Week-10 | Peer Review: Evaluate Peers' Contributions to Group Projects | Jay & Prashant |  | Not Started
| Week-11 | Conclusion and Recommendations | Jay & Prashant |  | Not Started
Milestone 5--Final Project Paper and Presentation | Week-12 | Create final Summary Documents & Presentation | Jay & Prashant |  | Not Started
| Week-12 | Peer Review: Evaluate Peers' Contributions to Group Projects | Jay & Prashant |  | Not Started